## Bug Report
Bug Report
|  |  | Project Name | Open Cart
|  |  | Created By | Muhammad Haris Tariq
|  |  | Created Date | 2026-07-09
Bug ID | Title | Description | Step to Reproduce | Expected Result | Actual Result | Severity | Priority | Bug Type | Environment | Status | Reported By
BUG_01 | User is able to log in using an invalid password | The application allows users to log in with an invalid password instead of rejecting the credentials. | 1.Navigate to the Login page. 2.Enter Email: abc@gmail.com in the Email field. 3.Enter Password: 54321 (invalid) in the Password field. 4.Click the Login button. | The application should reject the invalid password, display an appropriate error message (e.g., "Invalid email or password"), and should not log the user in. | The application logs the user in successfully even when an invalid password is entered. | Critical | High | Functional Bug | Chrome/Window 11 | Open | Muhammad Haris Tariq
BUG_02 | Application accepts email with leading/trailing spaces during login | The application allows users to log in successfully even when the email address contains leading or trailing spaces. | 1.Navigate to the Login page. 2.Enter Email: abc@gmail.com (with leading and trailing spaces). 3.Enter the correct password. 4.Click the Login button. | The application should automatically trim the leading and trailing spaces from the email or display an appropriate validation message. | The application displays the message "No match for email or password." | Medium | Medium | Functional Bug | Chrome/Window 11 | Open | Muhammad Haris Tariq
BUG_03 | Password field placeholder is missing | The Password field does not display the placeholder text on the Register page. | Navigate to the Register page. Observe the Password field. | The Password field should display the placeholder text "Enter Password" | The Password field does not display any placeholder text. | Low | Low | UI Bug | Chrome/Window 11 | Open | Muhammad Haris Tariq